## TOC
TestPlan and Test Design Outline for Buying VIP Services Project
Getting Started Tasks:
1. Gather all Business Requirement Documents(BRD), Specifications and Releases from Engineers (for each identified component write a short description of what it does and it's dependencies)
2. Make sure your Test Environment ready (New components build to Test Servers, Test Lab, Test Tools)
3. Know your Development and Test Team Members who will work with you on this Project
4. If were given Project on Design Stage - do Usability Review and ask which Components will be delivered first
5. What is the Build Acceptance Criteria - Able to do Basic Usecase from A-Z, otherwise reject build
6. Design Basic Usecases Diagram involving all New Components
7. Plan what Types of Tests you want to do, Prioritize them
8. Estimate Testing Time including cycles for Regression and Bug Fixes, Writing Test Documentation and Possible Automation
9. Know your Bugtracking system and where to submit bugs for this Project
10. Release Criteria and knowing your deadline
Drawing THE 'BIG PICTURE'
1. What kind of users come to these pages?
2. What are they trying to do?
3. How are they trying to do it?
4. What happens when they complete the process?
5. How many Web pages involved in this Project and what are they?
6. What Usecases you will pick as Top 3 (High Priority)?
7. Are these pages located on secure server? What tests can apply for basic security testing?
8. What are Minimum System Requirements for using these pages?
9. Test these pages at least on 2 Browser/OS Configurations
10. Test on at least 2-3 font sizes, and 2 screen resolutions
11. What are common error handling cases?
12. What is Client/Server Configuration?
13. What are the Testcases for Each Page?
14. Draw Usecases and Prepare Test Documentation
15. Do you need to setup any accounts for testing?
16. While testing, make sure all URLs coming from Test environment domain
Types of Test for this Project: | details | tester
Functionality | link
Security | link
Compatibility | link
User Interface | link
All Types of Tests | Check which tests | Priority | Time(Hours) | Cycles | Est. Hours
Release Acceptance Test
Functionality Testing
Ad Hoc Testing
UI Testing (Usability,Accessbility,look and Feel, Navigation Controls)
Usability
Logs review
Risk-Based(find big bugs first)
Server Tests (Stress, Load, Volume, Performance)
Compatibility/Configuration
Regression Testing
Integration
Forced Error Test/Error Handling
Documentation/Help (function and content)
Database and Data Testing
Flow
Data Import/Migration
3rd Party Integration
Security
Specification Verification
Install/Uninstall
Accessibility

## Functionality
Functionality Checklist
UserType and Scenario(Verify Succesful Purchase,Service Activation) | ACCT |  | Orderform |  |  | Login/Register |  | Checkout |  |  |  | Confirmation |  |  | DB | P/F
| YES | NO | 12m | 6m | 3m | Login | Register | Long |  |  | Short | FreeTrial | Charge | PayInfo | VIP
[8 empty] | CC | PP | MO
Logged In User buying 3m with CC |  | X |  |  | X |  |  | X |  |  |  | X |  |  | X
Logged In User with Existing Account | X |  |  | X | [6 empty] | X | X |  |  | X
Logged In VIP Upgrade | X |  | X | [7 empty] | X |  | X |  | X
Logged In User bying 6m with PayPal |  | X |  | X |  |  |  |  | X |  |  | None | None | X | None
Not Logged In User logging in buying |  | X |  |  | X | X |  | X |  |  |  | X |  |  | X
Not Logged In User Registering and buying with CC |  | X |  | X |  |  | X | X |  |  |  | X |  |  | X
Not Logged In User Registering and buying with Money Order |  | X | X |  |  |  | X |  |  | X |  | None | None | X | None
There are many more Usecases here…
…
Other Testcases including Error Handling from Client and Server Side: | [6 empty] | Pass/Fail
If there is a free trial make sure service is active,but no charge
Is there authorization fee?
Are onscreen instructions accurate?
Action command checks - Order, Submit, Add
Verify Login/Logout from New Pages
You can Divide Error Handling Cases on Client and Server Side
Are there Email Notifications?
Verify credit card validation and processing
Verify Handling of forgotten passwords
Verify Proper email Notifications and context
What Service used for CC credit validation and processing, test it
Does the application memorize your last selection, when leaving the page, what is expected?
Look for Errors in ordering/purchasing calculation
Look for more Error handling cases and Testcases in scripts (like cc.js - which manage Credit Card acceptance):
Ignoring credit card classification(cc doesn't match type)
Accepting expired Credit Card
Accepting Invalid Credit Card Numbers
Incorrect content of automated email reply
No intelegence in address verification(ZIP only)
If there is an issue with Billing Server proper message should be fetched
There have to be a time limit for the form to log you out if not in use and left open
Check Cookies, is there any secure info saved?
Should not be able to order package you already have again
Does the product allow users to recover gracefully from mistakes?
Is there a limit for login mistakes?
Are error messages friendly and consistent?
Double Click on Checkout/Order - sholldn't be charged twice
While Registering enter existing username, what is the expected result?
There should be warning when leaving unprocessed Checkout page

## Security
Security Checklist
Web security flaws may be caused by server configuration problems, poor design, and/or poor programming of web site scripts.
Pages
# | Testcases | Order | Login | Checkout | Confirm | Cookies | Profile
1 | Verify all calls for Secure Forms go through https | X | X | X | X
2 | If https-> then certificate require for the server | X | X | X | X
3 | Verify Secure info should be encrypted |  | X | X
4 | Check Cookies, is there any secure info saved? |  |  |  |  | X
5 | What is a validation method for authentication of user? | X | X | X | X |  | X
6 | What authenticated user autorized(permitted) to do? (give example on unix system) | X |  | X | X |  | X
7 | Make sure no secure info stored after user closed browser | [5 empty] | X
8 | Make sure no secure info stored after user logged out | [5 empty] | X
9 | Verify Able to Order and use Service when default 'Secure' Settings are set in a Browser(Internet Options/Advanced Tab/Security) | X | X | X | X | X | X
10 | Client SSL protocols(Secure Socket layer) should be enabes in a browser settings to accept HTTPS requests(Internet Options/Advanced Settings) | X | X | X | X | X | X
11 | Do View Source on all secure pages (sometimes info that is encrypted on the page is visible in a source)-last 4 digits of CC |  | X | X | X | X | X
12 | Verify no secure info sent in a Location Bar | X | X | X | X | X | X
13 | Try to bypass security by copying URL’s | X | X | X | X | X | X
Extras:
1.Test to ensure that username and password are not stored in user’s registry database or configuration files such as .INI files
2. Shouldn't be able to browse webserver directories and retrieve files
3. If there are any api calls updating DB password, username and sometimes session should be required
4. Sometimes companies block Certain IP addresses and sites - does your service works there, port 80 usually open, it can be a work around
5. Injections:
XML Injection, Javascript Injection, Cookie Injection
"SQL Injection" is subset of the unverified/unsanitized user input vulnerability. The idea is to convince the application to run SQL code that was not intended. These verification procedures must be carried out for all parameters that might be used to frame a database query. One solution is to escape out all special characters and ensure that query arguments appear within quotation marks. This solution prevents the SQL command interpreter from interpreting special characters as SQL elements.
These are the special characters to be monitored: ' " , ; ( ) Key SQL characters: FROM LIKE WHERE
More on SQL Injection: http://www.unixwiz.net/techtips/sql-injection.html
Samples are provided to allow reader to get basic idea of a potential attack and almost every section includes a brief information about itself. More :http://ferruh.mavituna.com/sql-injection-cheatsheet-oku/

## Compatibility
Compatibility Checklist
Performance requirements, minimum system requirements, supported hardware/software-determined at the beginning of product development-are used as a baseline to determine which testcases and test to write.
Testcases | Client System Configuration
Operating System
| Windows XP |  |  | Windows Vista |  |  | Mac OS
| Browser |  |  | Browser |  |  | Browser
| IE6 | IE7 | Firefox | IE6 | IE7 | Firefox | Safari | Firefox
1. Verify all pages look good, forms visible and accessible, alt tags
Orderform
Login/Registration
Checkout
Confirmation
2. Do few Usecases that change Pages Display also complete various Ordering cases and verify display of all components and function
Ordering With Credit Card
Ordering With Money Order
Ordering an Upgrade for the Service
Error handling for invalid Credit Card Info
Error handling for insufficient funds
Required Fields validation
3.Verify Pages look good on various screen resolutions, also resize windows
Orderform
Login/Registration
Checkout
Confirmation
4. Verify Pages look good on various Fonts (use CTRL++)
Orderform
Login/Registration
Checkout
Confirmation
5. Test with Various Browser Settings (Verify succesful ordering)
General Settings(Vary colors, fonts, and accessibility options)
Security Settings
Privacy Settings
Advanced Settings
Cookies Settings
6. Once released to Production use this ite for verification http://browsershots.org/
Other:
ServerSide Configuration - If various Servers used Solaris, Linix for content distribution ,make sure your application or program sucessfully runs on both
Turn ON/Off popup blockers
Possible Operating Systems
Windows
MAC
Unix
Linux
Palm OS, Windows Mobile
Communication Components
Browser
E-mail
Chat
FTP
Plugins
Flash
Windows Media Player
Real Player
Connectivity
Dial-Up
DSL
T1
Hardware
CPU
RAM
Graphic Display Card
Video Capture Card
Sound Card
Monitor
Input device (mouse, joystick)

## UI
Website User Interface Checklist
| Clear cache and cookies prior to testing | Test Pages
# | Testcases | Orderform | Login/ Registration | Checkout | Confirm
1 | Test all UI controls look as expected and function properly, this entails checking: -for the existence of UI controls on each page, window or dialog box; -checking if the default state (such as enable, disable,highlighted..) is as intended; -checking if the default value or selected mode is as intended; -checking if the tab order is intended -checking if the behavior of shortcuts(CTRL-X,CTRL-V) and other access keys (ALT-O-for Open) is as intended
2 | Textbox, Scrolling text box
3 | Checkboxes
4 | Radio buttons
5 | Dropdown menus
6 | Push buttons
7 | Images, Image Map
8 | Mouse Over Text(Alt Tags)
9 | Text Links
10 | Image-Links
Dynamic UI Controls
11 | Javascript
12 | CSS
13 | Ajax
14 | ActiveX
15
16 | Forms
17 | Fields size, type of accepted values:we had a bug when page crashed after entering 16 char in zip(db allowed only 15, but web 30)
18 | Required fields have to be marked
19 | Test default values for pages
20 | Are there Steps -1,2,3? Verify
21 | Test Navigation Tabs
22 | Basic controls, such as backward and forward navigation, zoom-in and zo0m-out, content refreshing check
23 | Shouldn't be able to go back to checkout after succesful order
24 | Tables
25 | Review Error Pages
26 | Testing Process flow (test proper redirects after login/register/buying)
27 | Verify links on Checkout Page shouldn't open new pages replacing checkout, but should open in a new window/tab
28 | If failed order should be able to go back and re-enter new card
29 | Login/Logout from all pages
30 | Are there any popups, all have to be tested and hosted on secure server
31 | Page Titles
32 | Pay attention to Application Instances
Type in each of the entry fields illegal SQL chars like : \ backslash,/ slash,: colon, * asterisk, ? Question mark, ><, ¦ pipe
Other interesting chars: !@#$%^&*()_+=
If you involved in Testing when Product is in Design phase review following:
Is the design approach natural for the target audience?
Is the design approach intuitive for the target audience?
Is the design approach consistently applies through the application?
Does the “look-and-feel” appeal to the target audience?
How and when will “Usability” tests be done?
Do graphics and text load as required?
Some Basic Errors you may find: -Broken Links -Missing Images -Wrong Links -Wrong Images -Correct links with no or outdated content -If CSS used - Visually test all Web Pages with all supported browsers *Use HTML link checker and HTML validation tools -spelling errors -extra or missing HTML tags -image syntax error -table tag errors -form input types and variables -graphics load time
If it is XHTML document, check:
Attribute names must be in lower case
Attribute values must be quoted
Attribute minimization is forbidden
The id attribute replaces the name attribute
The XHTML DTD defines mandatory elements
Navigation Design Issues:
Is the navigation intuitive?
Does it flow well?
Is accessibility of commonly used feature consistent throughout the program?
Can users tell where they are?
Do navigation conventions remain the same throughout the application(navbars, menus,nyperlinks)?
Examine application for consistent use of ‘mouse-over popups’, single clicks, double clicks and object dragging. Do results different from screen to screen?
Do keyboard alternatives for navigation including Enter and Tab keys- remain steady throughout the application?
Click the Tab button repeatedly and examine the highlight path that is created. Is it logical and consistent?

## Accessibility
Accessibility testing for different users
1. Select a random sampling of pages to test (popular ones)
2. Use a graphical browser to test (Opera is good, also other accessibility testing extensions in browsers)
3. View pages without images
4. View pages without style sheets
6. Check that your pages allow users to vary font sizes displayed
7. View the website with new technologies turned off (javascript, Java, Flash)
8. Use a voice or text-only browser to test
9. Validate by standards from www.w3.org/WAI/eval/
10. Identify document requirements and levels
11. Proofread all content
12. Conduct usability tests with a diversity of users